## TIBER Deliverables
Quality checklist TIBER process |  |  | <Test name> | on track
Activities & Deliverables |  |  |  | done
issues
Generic Threat Landscape (GTL)
Threat Intell | lead | Version/ Date | Deliverables | Status
Latest final GTL shared with WTL (via TM) | TCT |  | Generic Threat Landscape document
Preparation Phase
Pre-launch | lead | Version/ Date | Deliverables | Status
TIBER Documentation shared | TCT |  | Mail to WTL incl. link to TIBER documentation:
Start meeting minutes log-file | WTL |  | Minutes document to log actions + decisions for each meeting. Note: Paper trail of a test is important
Pre-launch meeting | WTL |  | Meeting planned by WTL and/or CISO, accepted by TCT (= Test mgr + back-up and TI mgr) Minutes Log (actions + decisions for each meeting) updated
Create information sharing group (e.g. WhatsApp, Wire, Signal or other) | WTL |  | Information sharing group with WT and TCT
Password management alignment | WTL |  | n/a
DNB Code-naam shared | TCT |  | n/a
Create and align high level planning related to TIBER process | WTL |  | Draft high level planning for TIBER process
Check if TCT and WTL back-up are available during planned phases (e.g. no overlap in holidays) | WTL/TCT |  | Final draft high level planning, starting point for the TIBER test
Meeting (crash course) to get the TCT and WT on the same level of knowledge. | WTL |  | Meeting planned by WTL and/or CISO, accepted by TCT and WT. Minutes log updated
Procurement | lead | Version/ Date | Deliverables | Status
Create shortlist of potential TIP/RTP | WTL |  | No objection from TCT
Rfp in line with the TIBER framework | WTL |  | Rfp, not mandatory to be shared with TCT
Ensure consistency with Procurement Guidelines in the proposal from the TIP/RTP | WTL |  | n/a
Allignment with TCT regarding the procured TIP/RTP incl. CV check of each TI/RT member | WTL |  | n/a, TCT is willing to support if necessary
Add TIP and RTP to information sharing group | WTL |  | Information sharing group with WT and TCT, extended with TIP and RTP
Create and align detailed planning with TIP and RTP | WTL |  | Detailed planning for TIBER Test and Closure phase
Scoping | lead | Version/ Date | Deliverables | Status
Scoping document (draft) based on format | WTL |  | Draft Scoping document
Scoping document reviewed by TCT | TCT |  | Feedback iterations from TCT to WTL to finalise scoping doc.
Check on scoping with Supervisor and/or Oversight (DNB expertise team) | TCT |  | Meeting with supervisor and/or oversight to agree on critical functions and underlying systems and services.
Attestation from C-level on scoping document | WTL |  | Documented attestation from C-level on scoping document
Scoping meeting. To explain scope (CF's and CIA) to TIP/RTP. Note: could be combined with launch meeting | WTL |  | Meeting accepted by WT, TCT, TIP, RTP, C-level could join. Minutes log updated
Scoping document (final) based on format | WTL |  | Final Scoping document incl. attestation
Launch
Launch meeting. To formally start the test phase. Note: could be combined with scoping meeting | WTL |  | Meeting, accepted by WT, TCT, TIP, RTP, C-level could join. Formal GO is part of the agenda. Minutes log updated
Formal GO after launch meeting to start the test phase | WTL |  | Minutes confirm the GO, pre-condition: attestation from c-level + detailed planning approved + exepectations managed
GO/ NO GO, to start the next phase | TCT
Test Phase
Threat Intel (6w) | lead | Version/ Date | Deliverables | Status
Weekly update meetings | WTL |  | Meeting, accepted by WT, TCT, TIP, RTP. Minutes log updated.
Discussion by WT and TIP about business overview (to be used as input for TTI Report) | TIP |  | Meeting, accepted by WT and TIP, TI mgr (from TCT) could join
Manage TTI report expectations, linked to GTL content | TIP |  | Meeting, accepted by TI mgr (from TCT) andTIP, WTL could join
First draft TTI report based on format, for review (after 2 à 3 weeks) | TIP |  | Draft TTI report based on format
Finalising TTI Report (after 4-6 weeks) | TIP |  | Feedback iterations from TCT to TIP to finalise TTI report. Final TTI Report based on format
Formal approval TTI Report | TCT |  | Mail from TCT to WTL to agree on the final TTI Report
Workshop: handover TTI report, discuss and choose scenarios and initiate the Test plan | WTL |  | Meeting, accepted by WT, TCT, TIP, RTP, C-level could join. Minutes log updated, confirming chosen scenario 1, 2 and possibilities for scenario X
GO/ NO GO, to start the next phase | TCT
Set up test plan (2w) | lead | Version/ Date | Deliverables | Status
Set up Test Plan (final) based on format | RTP |  | Final Test Plan making use of MITRE ATT@CK, incl. elaborated scenario 1 and 2
Check the systems that are in scope | WTL |  | n/a
Formal approval Test Plan | TCT |  | Mail from TCT to WT to start the test plan
Prepare leg ups | RTP |  | Preparation in advance where leg ups are or might be expected (eg: laptops as entry points, physical network plugins)
Inform C-level on planned attack scenarios | WTL |  | n/a
Agree on Test plan in a meeting to start the RT phase | TCT |  | Meeting, accepted by WT, TCT, TIP, RTP and C-level could join. Minutes log updated, confirming execution Test Plan/ start RT phase
GO/ NO GO, to start the next phase | TCT
Start RT phase (10-12w or more) | lead | Version/ Date | Deliverables | Status
Weekly meetings during RT phase | WTL |  | Meeting, accepted by WT, TCT, RTP and TIP could join. Minutes log updated
Provide documented updates upfront the weekly meetings incl. agenda. Content to be discussed during the meeting | RTP |  | Content includes: a) current position within timeline b) actions taken since last meeting c) flags captured since last meeting d) leg ups received since last meeting e) risk tracker including taken mitigation measures
Finalise scenario X (after 6 weeks) | WTL |  | Meeting, accepted by WT, TCT, TIP, RTP and C-level could join. Minutes log updated, confirming the RTP will elaborate the chosen scenario X.
Add scenario X to complete final Test Plan | RTP |  | Final Test Plan completed, incl. elaborated scenario X
Outplan for each flag (before capture) | RTP |  | Three outplan documents (if through fase is successfully finished)
Closure Phase (6w)
Closure | lead | Version/ Date | Deliverables | Status
RT report (final) based on format | RTP |  | Final RT report (review based on format TCT)
BT report (final draft) | BT |  | BT report
Kick off Purple Team sessions | WTL |  | Meeting, at least accepted by BT, WT, TTIP, RTP, and partially TCT (introducing TIBER-testing)
Start Remediation Plan for FI | WTL |  | Not mandatory to be shared with TCT
Board meeting/attestation (meeting with involved c-level(s) | WTL |  | Meeting, at least accepted by c-level, WTL and/or CISO, (TIP, RTP optional) and TCT. Minutes log updated
Distribute '360-feedback format' to WT, TIP and RTP to be filled in before the 360-feedback meeting. | TCT |  | Mail to WT, TIP and RTP, with the latest '360-feedback format'
360-feedback meeting | TCT |  | Meeting, at least accepted by WTL, TIP, RTP and TCT. BT may be represented. Minutes log updated
360-feedback report (final) based on format | TCT |  | Final draft 360-feedback document
Kill the information sharing group after saving passwords (e.g. WhatsApp, Wire, Signal or other) and check if all remaining malware etc has been eradicated. Also the providers should prove to have deleted all data and findings etc. of the test. | WTL |  | n/a
TCT and WTL discuss what could be interesting to share in the next WTL meeting | WTL |  | n/a
Test Summary (final) based on format | WTL |  | Final Test Summary
End of test, discharge WT | WTL