## Sheet1
ID | Activity_Code | T2_Actor | Activity_name | Duration | Start_Date_Time | Finish_Date_Time
3 | T2.PREP.T2O.PCDP1 | T2O | Pre-check DP + RTGS directory and CLM repository provisioning (full) | 120 mins | 08 February 2023 10:00 | 08 February 2023 12:00
4 | T2.PREP.CB.NMT1 | ALL CBs | CBs submit a first version of their NMT for validation | 0 mins | 08 February 2023 17:00 | 08 February 2023 17:00
5 | T2.PREP.T2O.NMT.RCP | T2O | 4CB confirm receipt of all NMTs (first version) | 0 mins | 08 February 2023 17:00 | 08 February 2023 17:00
6 | T2.PREP.T2O.PCDP2 | T2O | Pre-check DP + RTGS directory and CLM repository provisioning (full) | 120 mins | 15 February 2023 17:00 | 15 February 2023 19:00
7 | T2.PREP.T2O.PCDP3 | T2O | Pre-check DP + RTGS directory and CLM repository provisioning (full) | 120 mins | 22 February 2023 17:00 | 22 February 2023 19:00
8 | T2.PREP.T2O.CLM.RTGS.CHN.CLOSE | T2O | Closing of U2A and A2A CLM/RTGS channels | 0 mins | 28 February 2023 17:00 | 28 February 2023 17:00
9 | T2.PREP.T2O.PCDP4 | T2O | Pre-check DP + RTGS directory and CLM repository provisioning (full) | 120 mins | 01 March 2023 17:00 | 01 March 2023 19:00
10 | T2.PREP.T2O.PCDP5 | T2O | Pre-check DP + RTGS directory and CLM repository provisioning (full) | 120 mins | 08 March 2023 17:00 | 08 March 2023 19:00
11 | T2.PREP.ALL.CRDMCO | ALL T2Ps | Cut-off for CRDM changes incl. accounts/BICs for T2S and TIPS | 0 mins | 09 March 2023 17:00 | 09 March 2023 17:00
12 | T2.PREP.T2O.RTGS.CLM.DIR | T2O | Last RTGS directory and CLM repository provisioning (full version of RTGS directory that T2Ps should include in internal systems) | 15 mins | 10 March 2023 10:00 | 10 March 2023 10:15
13 | T2.PREP.T2O.DATA.PC | T2O | Final Pre-Check before DP | 60 mins | 10 March 2023 10:00 | 10 March 2023 11:00
14 | T2.PREP.T2O.DP.FINAL | T2O | Final (real) data propagation to CLM/RTGS (including activation) | 60 mins | 10 March 2023 11:00 | 10 March 2023 12:00
15 | T2.PREP.CB.NMT.FINAL | ALL CBs | CBs submit their final NMT | 0 mins | 10 March 2023 16:00 | 10 March 2023 16:00
16 | T2.PREP.T2O.NMT.VAL | T2O | 4CB confirm validation of all NMTs | 0 mins | 10 March 2023 17:00 | 10 March 2023 17:00
17 | T2.PREP.T2O.A2A.OPN1 | T2O | Inbound A2A RTGS channel opened | 0 mins | 11 March 2023 07:30 | 11 March 2023 07:30
18 | T2.PREP.T2P.PMV1 | ALL T2Ps | Pre-Migration validation tests | 120 mins | 11 March 2023 08:00 | 11 March 2023 10:00
19 | T2.PREP.T2P.RPT1 | ALL T2Ps | T2P report to their NSD issues detected during the pre-migration validation tests | 180 mins | 11 March 2023 08:00 | 11 March 2023 11:00
20 | T2.PREP.T2O.PMV.LLI1 | T2O | Closing of inbound A2A RTGS channel. T2 Operator assessment of the reported issues and preparation for the necessary LLI | 210 mins | 11 March 2023 10:00 | 11 March 2023 13:30
21 | T2.PREP.T2O.A2A.OPN2 | T2O | Inbound A2A RTGS channel opened | 0 mins | 11 March 2023 13:30 | 11 March 2023 13:30
22 | T2.PREP.T2P.PMV1.1 | ALL T2Ps | T2P re-execute trial test after LLI | 60 mins | 11 March 2023 13:30 | 11 March 2023 14:30
23 | T2.PREP.T2O.A2A.CLOSE2 | T2O | Inbound A2A RTGS channel closed | 0 mins | 11 March 2023 14:30 | 11 March 2023 14:30
24 | T2.PREP.T2O.A2A.OPN3 | T2O | Inbound A2A RTGS channel opened | 0 mins | 13 March 2023 07:00 | 13 March 2023 07:00
25 | T2.PREP.T2P.PMV2 | ALL T2Ps | Pre-Migration validation tests | 180 mins | 13 March 2023 07:30 | 13 March 2023 10:30
26 | T2.PREP.T2P.RPT2 | ALL T2Ps | T2P report to their NSD issues detected during the pre-migration validation tests | 240 mins | 13 March 2023 07:30 | 13 March 2023 11:30
27 | T2.PREP.T2O.PMV.LLI2 | T2O | Closing of inbound A2A RTGS channel. T2 Operator assessment of the reported issues and preparation for the necessary LLI | 270 mins | 13 March 2023 10:30 | 13 March 2023 15:00
28 | T2.PREP.T2O.A2A.OPN4 | T2O | Inbound A2A RTGS channel opened | 0 mins | 13 March 2023 15:00 | 13 March 2023 15:00
29 | T2.PREP.T2P.PMV2.1 | ALL T2Ps | T2P re-execute trial test after LLI | 120 mins | 13 March 2023 15:00 | 13 March 2023 17:00
30 | T2.PREP.T2O.CLOSE3 | T2O | Inbound A2A RTGS channel closed | 0 mins | 13 March 2023 17:00 | 13 March 2023 17:00
31 | T2.MW.T2O.GL.AS | T2O | Send last TARGET2/TIPS GL file and account statements | 35 mins | 17 March 2023 18:40 | 17 March 2023 19:15
33 | MWCP0 | ALL | MWCP0 - Start of Migration Weekend | 10 mins | 17 March 2023 19:15 | 17 March 2023 19:25
34 | T2.MW.T2O.TAR2.DISC | T2O | Technical connectivity | 1070 mins | 17 March 2023 19:25 | 18 March 2023 13:15
35 | T2.MW.T2O.TAR2.DISC | T2O | TARGET2 disconnected from T2S and TIPS | 90 mins | 17 March 2023 19:25 | 17 March 2023 20:55
36 | T2.MW.T2O.T2.CON | T2O | T2 connected to T2S and TIPS | 90 mins | 17 March 2023 20:55 | 17 March 2023 22:25
37 | T2.MW.CB.ESMIG | ALL CBs | CB connect internal systems to ESMIG | 375 mins | 17 March 2023 19:25 | 18 March 2023 01:40
38 | T2.MW.T2P.ESMIG | ALL T2Ps | T2P connect internal systems to ESMIG | 1070 mins | 17 March 2023 19:25 | 18 March 2023 13:15
49 | T2.MW.CB.MR.CSV | T2O | Confirmation that the csv files for the Minimum Reserves have been received | 0 mins | 17 March 2023 21:15 | 17 March 2023 21:15
50 | MWCP1 | ALL | MWCP1 - Green light to start MBT | 10 mins | 17 March 2023 21:15 | 17 March 2023 21:25
52 | T2.MW.T2O.MBT | T2O | Migration of Balances tool (including corrective measures, internal checks and reopening of U2A channels for CLM/RTGS) | 210 mins | 17 March 2023 21:25 | 18 March 2023 00:55
73 | T2.MW.CB.CL.REC | NL-CB | CB reconciliation of migrated credit lines | 60 mins | 18 March 2023 00:55 | 18 March 2023 01:55
79 | T2.MW.T2O.CL.REP | T2O | Credit lines repair | 60 mins | 18 March 2023 00:55 | 18 March 2023 01:55
100 | T2.MW.CB.BR | NL-CB | CB balance reconcilliation | 120 mins | 18 March 2023 01:55 | 18 March 2023 03:55
106 | T2.MW.T2P.BL.REP | T2O | Repair balances | 180 mins | 18 March 2023 00:55 | 18 March 2023 03:55
107 | MWCP2 | ALL | MWCP2 - MBT process completed and start of CSOD RSOD | 10 mins | 18 March 2023 03:55 | 18 March 2023 04:05
108 | T2.MW.T2O.CSOD.RSOD | T2O | CLM & RTGS Start of Business Day | 15 mins | 18 March 2023 04:05 | 18 March 2023 04:20
109 | T2.MW.T2O.A2A.OPEN | T2O | Opening of A2A channels for CLM/RTGS | 15 mins | 18 March 2023 04:20 | 18 March 2023 04:35
110 | T2.MW.T2O.T2.T2S.TIPS.CONFIRM | T2O | Confirmation of the connection T2 with T2S and TIPS | 0 mins | 17 March 2023 22:25 | 17 March 2023 22:25
111 | MWCP3 | ALL | MWCP3 - T2O confirm CSOD/RSOD is complete, T2S and TIPS is connected, A2A channel opens | 10 mins | 18 March 2023 04:35 | 18 March 2023 04:45
138 | MWCP4 | ALL | MWCP4 - CBs agree to initiate CRTI | 10 mins | 18 March 2023 06:45 | 18 March 2023 06:55
139 | T2.MW.T2O.CRTI | T2O | Start of CLM RTS | 0 mins | 18 March 2023 06:55 | 18 March 2023 06:55
160 | T2.MW.CB.CBO | NL-CB | CBO U2A and A2A execution | 30 mins | 18 March 2023 06:55 | 18 March 2023 07:25
186 | T2.MW.CB.SF.REC.REP | NL-CB | Reconciliation of the reimbursement of the SF, related interest calculation, CBO and Repairs | 30 mins | 18 March 2023 07:55 | 18 March 2023 08:25
192 | MWCP5 | ALL | MWCP5 - CBs confirm reconciliation/CBO activities and agree to initiate CESO and RRTI | 10 mins | 18 March 2023 09:55 | 18 March 2023 10:05
193 | T2.MW.T2O.RRTI.CESO | T2O | Processing of CLM standing orders and LT | 30 mins | 18 March 2023 10:05 | 18 March 2023 10:35
214 | T2.MW.CB.CLM.SO.REC | NL-CB | Reconciliation of CLM Standing Orders and LT (optional) | 30 mins | 18 March 2023 10:35 | 18 March 2023 11:05
220 | MWCP6 | ALL | MWCP6 - CBs agree to initiate RESO | 10 mins | 18 March 2023 11:35 | 18 March 2023 11:45
221 | T2.MW.T2O.RESO | T2O | Processing of RTGS standing orders | 15 mins | 18 March 2023 11:45 | 18 March 2023 12:00
222 | MWCP7 | ALL | MWCP7 - T2O Confirm RESO and CBs start reconciliation of SO | 10 mins | 18 March 2023 12:00 | 18 March 2023 12:10
243 | T2.MW.CB.RTGS.SO.REC | NL-CB | Reconciliation of RTGS Standing Orders and LT (optional) | 0 mins | 18 March 2023 12:10 | 18 March 2023 12:10
268 | T2.MW.CB.REQ.GL | NL-CB | CB request green light to start T2P activities | 0 mins | 18 March 2023 12:10 | 18 March 2023 12:10
293 | T2.MW.ECB.GRANT.GL | NL-CB | ECB grants green light to CB | 0 mins | 18 March 2023 12:15 | 18 March 2023 12:15
318 | T2.MW.CB.GL.T2P | NL-CB | CB gives green light to T2Ps | 0 mins | 18 March 2023 12:20 | 18 March 2023 12:20
324 | MWCP8 | ALL | MWCP8 - All CBs have given green light to T2Ps | 10 mins | 18 March 2023 13:10 | 18 March 2023 13:20
325 | T2.MW.CB.T2P.ALL.GL | ALL CBs | CBs green light to T2Ps (for CBs that have not given the green light prior) | 10 mins | 18 March 2023 13:20 | 18 March 2023 13:30
346 | T2.MW.T2P.BAL.REC | NL-T2Ps | T2P balance reconciliation (optional) | 240 mins | 18 March 2023 13:30 | 18 March 2023 17:30
371 | T2.MW.T2P.SO.REC | NL-T2Ps | T2P standing orders reconciliation (conditional and optional) | 240 mins | 18 March 2023 13:30 | 18 March 2023 17:30
396 | T2.MW.T2P.LT | NL-T2Ps | T2P liquidity transfers (optional) | 240 mins | 18 March 2023 13:30 | 18 March 2023 17:30
402 | MWCP9 | ALL | MWCP9 - Green Light for T2S NTS and maintenance window | 10 mins | 18 March 2023 17:30 | 18 March 2023 17:40
403 | T2.MW.T2O.MW | T2O | Maintenance window (may start earlier with earlier end of T2S NTS) | 600 mins | 18 March 2023 21:00 | 19 March 2023 07:00
404 | T2.MW.T2O.RTSII | T2O | RTGS RTS II start | 15 mins | 19 March 2023 07:15 | 19 March 2023 07:30
405 | MWCP10 | ALL | MWCP10 - 4CB confirm start of RTGS RTS II | 10 mins | 19 March 2023 07:50 | 19 March 2023 08:00
406 | T2.MW.T2P.RTS2.PVW1 | ALL T2Ps | Start of Payment validation window | 120 mins | 19 March 2023 08:00 | 19 March 2023 10:00
407 | T2.MW.T2O.A2A.CLO | T2O | U2A and A2A channels closed for CLM/RTGS | 0 mins | 19 March 2023 10:00 | 19 March 2023 10:00
408 | T2.MW.T2O.PVW.LLI | T2O | Operator intervention for payments blocked by incorrect DN or PTA | 120 mins | 19 March 2023 10:00 | 19 March 2023 12:00
409 | T2.MW.T2O.A2A.OPN | T2O | U2A and A2A channels will be reopened for CLM/RTGS | 30 mins | 19 March 2023 12:00 | 19 March 2023 12:30
410 | T2.MW.T2P.RTS2.PVW2 | ALL T2Ps | T2P re-execute trial tests after LLI | 30 mins | 19 March 2023 12:30 | 19 March 2023 13:00
411 | MWCP11 | ALL | MWCP11 - End of Migration Weekend activities | 15 mins | 19 March 2023 13:00 | 19 March 2023 13:15