## Calendar external
Week number | Day/ Week/ Weekend | Start Date | End Date | Activity type | Activities | Comments
51 | Week | 2022-12-12 | 2022-12-16 | Special testing | T2-T2S CSLD cross border tests
51 | Day | 2022-12-13 | 2022-12-13 | ORT | T2-T2S CSLD ORT - ECONSII test with participants (one-day opening scenario)
51 | Day | 2022-12-14 | 2022-12-15 | Special testing | Volume Test | DECB participant
51 | Day | 2022-12-15 | 2022-12-15 | Special testing | Open ECONSII from 9.00 - 13.00 CET
51 | Day | 2022-12-16 | 2022-12-16 | Schedule | T2-T2S synchronised release day
51 | Day | 2022-12-16 | 2022-12-16 | Release deployment | CSLD Deployment
52 | Week | 2022-12-19 | 2022-12-22 | Schedule | T2-T2S synchronised standard day
52 | Day | 2022-12-22 | 2022-12-22 | Special testing | Open ECONSII from 9.00 - 13.00 CET
52 | Day | 2022-12-23 | 2022-12-23 | Schedule | T2-T2S synchronised release day
52 | Day | 2022-12-23 | 2022-12-23 | Release deployment | CSLD Deployment
53 | Day | 2022-12-26 | 2022-12-26 | Schedule | T2 Closing day
53 | Week | 2022-12-27 | 2022-12-29 | Schedule | T2-T2S synchronised standard day
53 | Day | 2022-12-29 | 2022-12-29 | Special testing | Open ECONSII from 9.00 - 13.00 CET
53 | Day | 2022-12-30 | 2022-12-30 | Schedule | T2-T2S synchronised release day
1 | Day | 2023-01-02 | 2023-01-05 | Schedule | T2-T2S synchronised standard day
1 | Day | 2023-01-05 | 2023-01-05 | Special testing | Open ECONSII from 9.00 - 13.00 CET
1 | Day | 2023-01-06 | 2023-01-06 | Schedule | T2-T2S synchronised release day
1 | Day | 2023-01-06 | 2023-01-06 | Release deployment | CSLD Deployment
2 | Day | 2023-01-09 | 2023-01-12 | Schedule | T2-T2S synchronised standard day
2 | Week | 2023-01-09 | 2023-01-13 | Special testing | T2-T2S CSLD BILL testing campaign
2 | Day | 2023-01-12 | 2023-01-12 | Special testing | Open ECONSII from 9.00 - 13.00 CET
2 | Day | 2023-01-13 | 2023-01-13 | Schedule | T2-T2S synchronised release day
2 | Day | 2023-01-13 | 2023-01-13 | Release deployment | CSLD Deployment
3 | Week | 2023-01-16 | 2023-01-20 | Special testing | T2-T2S CSLD BILL testing campaign
3 | Week | 2023-01-16 | 2023-01-20 | Special testing | T2-T2S CSLD cross border tests
3 | Day | 2023-01-19 | 2023-01-19 | Special testing | Open ECONSII from 9.00 - 13.00 CET
3 | Day | 2023-01-20 | 2023-01-20 | Schedule | T2-T2S synchronised release day
4 | Week | 2023-01-23 | 2023-01-27 | Special testing | T2-T2S CSLD BILL testing campaign
4 | Day | 2023-01-26 | 2023-01-26 | Special testing | Open ECONSII from 9.00 - 13.00 CET
4 | Day | 2023-01-27 | 2023-01-27 | Schedule | T2-T2S synchronised release day
5 | Week | 2023-01-30 | 2023-02-03 | Special testing | T2-T2S CSLD BILL testing campaign
5 | Day | 2023-02-02 | 2023-02-02 | Special testing | Open ECONSII from 9.00 - 13.00 CET
5 | Day | 2023-02-03 | 2023-02-03 | Schedule | T2-T2S synchronised release day
5 | Day | 2023-02-03 | 2023-02-05 | Migration testing | T2-T2S CSLD UT MWDR
6 | Week | 2023-02-06 | 2023-02-10 | Special testing | T2-T2S CSLD BILL testing campaign
6 | Day | 2023-02-09 | 2023-02-09 | Special testing | Open ECONSII from 9.00 - 13.00 CET
6 | Day | 2023-02-10 | 2023-02-10 | Schedule | T2-T2S synchronised release day
7 | Day | 2023-02-16 | 2023-02-16 | Special testing | Open ECONSII from 9.00 - 13.00 CET
7 | Day | 2023-02-17 | 2023-02-17 | Schedule | T2-T2S synchronised release day
8 | Day | 2023-02-23 | 2023-02-23 | Special testing | Open ECONSII from 9.00 - 13.00 CET
8 | Day | 2023-02-24 | 2023-02-24 | Schedule | T2-T2S synchronised release day
9 | Day | 2023-03-03 | 2023-03-03 | Schedule | T2-T2S synchronised release day
10 | Day | 2023-03-10 | 2023-03-10 | Schedule | T2-T2S synchronised release day
11 | Day | 2023-03-17 | 2023-03-17 | Schedule | T2-T2S synchronised release day
12 | Day | 2023-03-24 | 2023-03-24 | Schedule | T2-T2S synchronised release day
13 | Day | 2023-03-31 | 2023-03-31 | Schedule | T2-T2S synchronised release day
14 | Day | 2023-04-03 | 2022-04-04 | Schedule | T2-T2S Synchronised Standard day
14 | Day | 2023-04-05 | 2023-04-05 | Schedule | T2-T2S Synchronised Standard day
14 | Day | 2023-04-06 | 2023-04-06 | Schedule | T2-T2S Synchronised Standard day
14 | Day | 2023-04-07 | 2023-04-07 | Schedule | T2 Closing day
15 | Day | 2023-04-10 | 2023-04-10 | Schedule | T2 Closing day
15 | Week | 2023-04-11 | 2023-04-13 | Schedule | T2-T2S synchronised standard day
15 | Week | 2023-04-14 | 2023-04-14 | Schedule | T2-T2S synchronised release day
16 | Week | 2023-04-17 | 2023-04-20 | Schedule | T2-T2S-ECMS synchronised standard day
16 |  | 2023-04-17 | 2023-04-21 | Special testing | ECMS and CLM interconnection
16 | Day | 2023-04-21 | 2023-04-21 | Schedule | T2-T2S-ECMS synchronised release day
17 | Week | 2023-04-24 | 2023-04-25 | Schedule | T2-T2S synchronised standard day
17 |  | 2023-04-24 | 2023-04-28 | Special testing | ECMS and CLM interconnection
17 | Day | 2023-04-26 | 2023-04-27 | Schedule | T2-T2S-ECMS synchronised standard day
17 | Day | 2023-04-28 | 2023-04-28 | Schedule | T2-T2S-ECMS synchronised release day
18 | Day | 2023-05-01 | 2023-05-01 | Schedule | T2S Closing day
18 |  | 2023-05-01 | 2023-05-05 | Special testing | ECMS and CLM interconnection
18 | Week | 2023-05-02 | 2023-05-04 | Schedule | T2-T2S-ECMS synchronised standard day
18 | Day | 2023-05-05 | 2023-05-05 | Schedule | T2-T2S-ECMS synchronised release day
19 | Day | 2023-05-08 | 2023-05-10 | Schedule | T2-T2S-ECMS synchronised standard day
19 |  | 2023-05-08 | 2023-05-12 | Special testing | ECMS and CLM interconnection
19 | Day | 2023-05-11 | 2023-05-11 | Schedule | T2-T2S-ECMS synchronised release day
19 | Day | 2023-05-12 | 2023-05-12 | Schedule | T2-T2S-ECMS synchronised standard day
20 | Day | 2023-05-19 | 2023-05-19 | Schedule | T2-T2S-ECMS synchronised release day
21 | Day | 2023-05-26 | 2023-05-26 | Schedule | T2-T2S-ECMS synchronised release day
22 |  | 2023-05-29 | 2023-06-02 | Special testing | ECMS and CLM interconnection
22 | Day | 2023-06-02 | 2023-06-02 | Schedule | T2-T2S-ECMS synchronised release day
23 |  | 2023-06-05 | 2023-06-09 | Special testing | ECMS and CLM interconnection
23 | Day | 2023-06-09 | 2023-06-09 | Schedule | T2-T2S-ECMS synchronised release day
24 | Day | 2023-06-16 | 2023-06-16 | Schedule | T2-T2S-ECMS synchronised release day
25 | Day | 2023-06-19 | 2023-06-19 | Schedule | T2-T2S-ECMS synchronised standard day
25 |  | 2023-06-19 | 2023-06-23 | Special testing | ECMS and CLM interconnection
25 | Day | 2023-06-20 | 2023-06-20 | Schedule | T2-T2S-ECMS synchronised standard day
25 | Day | 2023-06-21 | 2023-06-21 | Schedule | T2-T2S-ECMS synchronised standard day
25 | Day | 2023-06-22 | 2023-06-22 | Schedule | T2-T2S-ECMS synchronised standard day
26 |  | 2023-06-26 | 2023-06-30 | Special testing | ECMS and CLM interconnection
26 |  | 2023-06-26 | 2023-06-30 | Special testing | ECMS and T2S interconnection
26 | Weekend | 2023-07-01 | 2023-07-02 | Operational activity | IBM Z server migration
27 |  | 2023-07-03 | 2023-07-07 | Special testing | ECMS and CLM interconnection
27 |  | 2023-07-03 | 2023-07-07 | Special testing | ECMS and T2S interconnection
27 | Day | 2023-07-07 | 2023-07-07 | Schedule | T2-T2S-ECMS synchronised release day
27 | Weekend | 2023-07-08 | 2023-07-09 | Operational activity | IBM Z server migration
28 |  | 2023-07-10 | 2023-07-14 | Special testing | ECMS and CLM interconnection
28 |  | 2023-07-10 | 2023-07-14 | Special testing | ECMS and T2S interconnection
28 | Day | 2023-07-14 | 2023-07-14 | Schedule | T2-T2S-ECMS synchronised release day
28 | Weekend | 2023-07-15 | 2023-07-16 | Operational activity | IBM Z server migration
29 |  | 2023-07-17 | 2023-07-21 | Special testing | ECMS and CLM interconnection
29 |  | 2023-07-17 | 2023-07-21 | Special testing | ECMS and T2S interconnection
29 | Day | 2023-07-21 | 2023-07-21 | Schedule | T2-T2S-ECMS synchronised release day
29 | Weekend | 2023-07-22 | 2023-07-23 | Operational activity | IBM Z server migration
30 |  | 2023-07-24 | 2023-07-28 | Special testing | ECMS and CLM interconnection
30 |  | 2023-07-24 | 2023-07-28 | Special testing | ECMS and T2S interconnection
30 | Day | 2023-07-28 | 2023-07-28 | Schedule | T2-T2S-ECMS synchronised release day
30 | Weekend | 2023-07-29 | 2023-07-30 | Operational activity | IBM Z server migration
31 |  | 2023-07-31 | 2023-08-04 | Special testing | ECMS and CLM interconnection
31 |  | 2023-07-31 | 2023-08-04 | Special testing | ECMS and T2S interconnection
31 | Day | 2023-08-04 | 2023-08-04 | Schedule | T2-T2S-ECMS synchronised release day
31 | Weekend | 2023-08-05 | 2023-08-06 | Operational activity | IBM Z server migration
32 |  | 2023-08-07 | 2023-08-11 | Special testing | ECMS and CLM interconnection
32 |  | 2023-08-07 | 2023-08-11 | Special testing | ECMS and T2S interconnection
32 | Day | 2023-08-11 | 2023-08-11 | Schedule | T2-T2S-ECMS synchronised release day
33 | Day | 2023-08-14 | 2023-08-14 | Schedule | T2-T2S-ECMS synchronised standard day
33 |  | 2023-08-14 | 2023-08-18 | Special testing | ECMS and CLM interconnection
33 |  | 2023-08-14 | 2023-08-18 | Special testing | ECMS and T2S interconnection
33 | Day | 2023-08-15 | 2023-08-15 | Schedule | T2-T2S-ECMS synchronised standard day
33 | Day | 2023-08-16 | 2023-08-16 | Schedule | T2-T2S-ECMS synchronised standard day
33 | Day | 2023-08-17 | 2023-08-17 | Schedule | T2-T2S-ECMS synchronised standard day
34 |  | 2023-08-21 | 2023-08-25 | Special testing | ECMS and CLM interconnection
34 |  | 2023-08-21 | 2023-08-25 | Special testing | ECMS and T2S interconnection
34 |  | 2023-08-21 | 2023-08-25 | Schedule | T2-T2S-ECMS synchronised standard day
34 |  | 2023-08-21 | 2023-08-25 | Schedule | T2-T2S-ECMS synchronised release day
34 | Weekend | 2023-08-26 | 2023-08-27 | Operational activity | IBM Z server migration
35 |  | 2023-08-28 | 2023-09-01 | Special testing | ECMS and CLM interconnection
35 |  | 2023-08-28 | 2023-09-01 | Special testing | ECMS and T2S interconnection
35 |  | 2023-08-28 | 2023-09-01 | Schedule | T2-T2S-ECMS synchronised standard day
35 |  | 2023-08-28 | 2023-09-01 | Schedule | T2-T2S-ECMS synchronised release day
35 | Weekend | 2023-09-02 | 2023-09-03 | Operational activity | IBM Z server migration
36 |  | 2023-09-04 | 2023-09-08 | Special testing | ECMS and CLM interconnection
36 |  | 2023-09-04 | 2023-09-08 | Special testing | ECMS and T2S interconnection
37 |  | 2023-09-11 | 2023-09-15 | Special testing | ECMS and CLM interconnection
37 |  | 2023-09-11 | 2023-09-15 | Special testing | ECMS and T2S interconnection
38 |  | 2023-09-18 | 2023-09-22 | Special testing | ECMS and CLM interconnection
38 |  | 2023-09-18 | 2023-09-22 | Special testing | ECMS and T2S interconnection
38 | Day | 2023-09-21 | 2023-09-21 | Operational activity | upgrade to zOS 2.5
39 |  | 2023-09-25 | 2023-09-29 | Special testing | ECMS and CLM interconnection
39 |  | 2023-09-25 | 2023-09-29 | Special testing | ECMS and T2S interconnection
40 |  | 2023-10-02 | 2023-10-06 | Special testing | ECMS and CLM interconnection
40 |  | 2023-10-02 | 2023-10-06 | Special testing | ECMS and T2S interconnection
40 | Day | 2023-10-06 | 2023-10-06 | Schedule | T2-T2S-ECMS synchronised release day
41 | Day | 2023-10-09 | 2023-10-09 | Schedule | T2-T2S-ECMS synchronised standard day
41 |  | 2023-10-09 | 2023-10-13 | Special testing | ECMS and CLM interconnection
41 |  | 2023-10-09 | 2023-10-13 | Special testing | ECMS and T2S interconnection
41 | Day | 2023-10-10 | 2023-10-10 | Schedule | T2-T2S-ECMS synchronised standard day
41 | Day | 2023-10-11 | 2023-10-11 | Schedule | T2-T2S-ECMS synchronised standard day
41 | Day | 2023-10-12 | 2023-10-12 | Schedule | T2-T2S-ECMS synchronised standard day
41 | Day | 2023-10-13 | 2023-10-13 | Schedule | T2-T2S-ECMS synchronised release day
43 | Day | 2023-10-28 | 2023-10-28 | Operational activity | upgrade to zOS 2.5
52 | Day | 2023-12-25 | 2023-12-26 | Schedule | T2S Closing day
1 | Day | 2024-01-01 | 2024-01-01 | Schedule | T2S Closing day
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Week number = WEEKNUM([Start Date])