## Sheet1
ID | Activity_Code | T2_Actor | Activity_name | Duration | Start_Date_Time | Finish_Date_Time | Predecessors | Successors | Active?
3 | T2.PREP.ALL.CRDMCO | ALL | Cut-off for CRDM changes | 0 mins | 01 February 2023 15:00 | 01 February 2023 15:00 |  | 4FS+15m | Active
4 | T2.PREP.T2O.EOD | T2O | Start EOD 01/02/2023 | 60 mins | 01 February 2023 15:15 | 01 February 2023 16:15 | 3FS+15m | 5 | Active
5 | T2.PREP.T2.A2A.U2A.CLO | T2O | Closing of A2A and U2A channel for CLM/RTGS | 10 mins | 01 February 2023 16:15 | 01 February 2023 16:25 | 4 | 6 | Active
6 | T2.PREP.T2O.DEL | T2O | Deletion of T2-UTEST dynamic data | 180 mins | 01 February 2023 16:25 | 01 February 2023 19:25 | 5 | 7 | Active
7 | T2.PREP.T2O.CRDM.LOAD | T2O | Data propagation and CRDM loading to CLM/RTGS | 60 mins | 02 February 2023 07:00 | 02 February 2023 08:00 |  | 9 | Active
8 | T2.PREP.T2O.CRDM.ACTIV | T2O | Activation of CRDM reference data | 60 mins | 02 February 2023 08:00 | 02 February 2023 09:00 | 8 | 10 | Active
9 | T2.PREP.T2O.RTGS.CLM.DIR | T2O | Sending of RTGS directory and CLM repository | 10 mins | 02 February 2023 09:00 | 02 February 2023 09:10 | 9 |  | Active
10 | T2.PREP.T2.A2A.OPN1 | T2O | Opening of Inbound A2A RTGS channel | 30 mins | 02 February 2023 12:00 | 02 February 2023 12:30 |  | 12 | Active
11 | T2.PREP.T2P.PMV1 | ALL T2Ps | Pre-Migration validation tests | 240 mins | 02 February 2023 12:30 | 02 February 2023 16:30 | 11 | 13 | Active
12 | T2.PREP.T2.A2A.CLO2 | T2O | Closing of inbound A2A RTGS channel | 30 mins | 02 February 2023 16:30 | 02 February 2023 17:00 | 12 | 14,15 | Active
13 | T2.PREP.T2O.PMV.LLI | T2O | T2 Operator assessment of the reported issues and preparation for the necessary LLI | 60 mins | 02 February 2023 17:00 | 02 February 2023 18:00 | 13 |  | Active
14 | T2.PREP.T2O.PMV.LLI1 | T2O | LLI by the T2 Operator (Part 1) | 60 mins | 02 February 2023 17:00 | 02 February 2023 18:00 | 13 |  | Active
15 | T2.PREP.T2O.PMV.LLI2 | T2O | LLI by the T2 Operator (Part 2) | 60 mins | 03 February 2023 07:00 | 03 February 2023 08:00 |  | 17 | Active
16 | T2.PREP.T2.A2A.OPN2 | T2O | Opening of Inbound A2A RTGS channel | 30 mins | 03 February 2023 08:00 | 03 February 2023 08:30 | 16 | 18 | Active
17 | T2.PREP.T2P.PMV2 | ALL T2Ps | Pre-Migration validation re-test | 240 mins | 03 February 2023 08:30 | 03 February 2023 12:30 | 17 | 19 | Active
18 | T2.PREP.T2.A2A.CLO3 | T2O | Closing of inbound A2A RTGS channel | 30 mins | 03 February 2023 12:30 | 03 February 2023 13:00 | 18 |  | Active
45 | T2.PM.T2O.NMT.RCP | T2O | Confirmation of receipt of all NMTs | 0 mins | 30 January 2023 12:00 | 30 January 2023 12:00 | 21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,39,40,41,42,43,44,45 |  | Active
46 | T2.PM.T2O.NMT.VAL | T2O | Confirmation of validation of all NMT | 0 mins | 03 February 2023 12:00 | 03 February 2023 12:00 |  |  | Active
47 | T2.MW.T2O.GL.AS | T2O | Send last TARGET2 GL file and account statements | 35 mins | 03 February 2023 18:40 | 03 February 2023 19:15 |  |  | Active
49 | MWCP0 | ALL | MWCP0 - Start of Migration Weekend | 10 mins | 03 February 2023 19:15 | 03 February 2023 19:25 |  | 51,59,61,62,63,66,67,64,65,60,53 | Active
52 | T2.MW.T2O.TAR2.DISC | T2O | TARGET2 disconnected from T2S and TIPS | 90 mins | 03 February 2023 19:25 | 03 February 2023 20:55 | 50 | 54,131 | Inactive
53 | T2.MW.T2O.T2.CON | T2O | T2 connected to T2S and TIPS | 90 mins | 03 February 2023 20:55 | 03 February 2023 22:25 | 53 | 131,55 | Inactive
54 | T2.MW.CB.ESMIG | ALL CBs | CB connect internal systems to ESMIG | 375 mins | 03 February 2023 22:25 | 04 February 2023 04:40 | 54 | 127,56 | Inactive
55 | T2.MW.T2P.ESMIG | ALL T2Ps | T2P connect internal systems to ESMIG | 240 mins | 04 February 2023 04:40 | 04 February 2023 08:40 | 55 | 127,57 | Inactive
56 | T2S.MW.Deploy | T2O | Green light to start deployment (CR) | 0 mins | 04 February 2023 08:40 | 04 February 2023 08:40 | 56 |  | Inactive
67 | T2.MW.CB.MR.CSV | T2O | Confirmation that the csv files for the Minimum Reserves have been received | 0 mins | 03 February 2023 21:25 | 03 February 2023 21:25 | 58,59,60,61,62,63,64,65,66,354,355 | 68,70 | Active
68 | MWCP1 | ALL | MWCP1 - Data propagation completed and MR csv files submitted | 10 mins | 03 February 2023 21:25 | 03 February 2023 21:35 | 68 | 70 | Active
70 | T2.MW.T2O.CL.MIG | T2O | Migration of Balances tool | 90 mins | 03 February 2023 21:35 | 03 February 2023 23:05 | 68 | 74,75,76,77,78,79,80,81,82,83,84,85,86,87,88,89,90,91,92,93,94,95,96,97,98,99,100,72 | Active
71 | T2.MW.T2O.CL.MIG.Buffer | T2O | MBT possible corrective measures | 120 mins | 03 February 2023 23:05 | 04 February 2023 01:05 | 70 | 74,73,103,106,109,119,121,123,126 | Active
72 | T2.MW.T2.U2A.OPN | T2O | U2A channel opened for CLM/RTGS | 0 mins | 04 February 2023 01:05 | 04 February 2023 01:05 | 71
98 | T2.MW.T2O.CL.REP | T2O | Credit lines repair | 60 mins | 04 February 2023 01:05 | 04 February 2023 02:05 | 72 |  | Active
125 | T2.MW.T2P.BL.REP | T2O | Repair balances | 180 mins | 04 February 2023 01:05 | 04 February 2023 04:05 | 72 | 127 | Active
126 | MWCP2 | ALL | MWCP2 - MBT process completed and start of CSOD RSOD | 10 mins | 04 February 2023 04:05 | 04 February 2023 04:15 | 126,55,56,101,102,103,104,105,106,107,108,109,110,111,112,113,114,115,116,117,118,119,120,121,122,123,124,125,100 | 128 | Active
127 | T2.MW.T2O.BD.CHG | T2O | CLM & RTGS Start of Business Day | 15 mins | 04 February 2023 04:15 | 04 February 2023 04:30 | 127 | 132,130,129 | Active
129 | T2.MW.T2O.A2A.OPEN | T2O | Opening of A2A channel for CLM/RTGS | 15 mins | 04 February 2023 04:30 | 04 February 2023 04:45 | 128 |  | Active
130 | T2.MW.T2O.T2.CONFIRM | T2O | Confirmation of the connection T2 with T2S and TIPS | 0 mins | 03 February 2023 22:25 | 03 February 2023 22:25 | 53,54 | 132 | Inactive
131 | MWCP3 | ALL | MWCP3 - T2O confirm CSOD/RSOD is complete, T2S and TIPS is connected, A2A channel opens | 10 mins | 04 February 2023 04:30 | 04 February 2023 04:40 | 128,131 | 134,135,136,137,138,139,140,141,142,143,144,145,146,147,148,149,150,151,152,153,154,155,156,157,158 | Active
158 | MWCP4 | ALL | MWCP4 - CBs agree to initiate CRTI | 10 mins | 04 February 2023 06:40 | 04 February 2023 06:50 | 134,135,136,137,138,139,140,142,143,144,145,146,147,148,149,150,151,152,153,154,155,156,157,158 | 160 | Active
212 | MWCP5 | ALL | MWCP5 - CBs confirm reconciliation/CBO activities and agree to initiate CESO and RRTI | 10 mins | 04 February 2023 09:50 | 04 February 2023 10:00 | 134,135,136,137,138,139,140,141,142,143,144,145,146,147,148,149,150,151,152,153,154,155,156,157,158,188,189,190,191,192,193,194,195,196,197,198,199,200,201,202,203,204,205,206,207,208,209,210,211,212 | 214 | Active
213 | T2.MW.T2O.CESO | T2O | Processing of CLM standing orders | 30 mins | 04 February 2023 10:00 | 04 February 2023 10:30 | 213 | 216,217,218,219,220,221,222,223,224,225,226,227,228,230,231,232,233,234,235,236,237,238,239,240,229 | Active
240 | MWCP6 | ALL | MWCP6 - CBs agree to initiate RESO | 10 mins | 04 February 2023 11:30 | 04 February 2023 11:40 | 216,217,218,219,220,221,222,223,224,225,226,227,228,230,231,232,233,234,235,236,237,238,239,240,229 | 242 | Active
241 | T2.MW.T2O.RRTI.RESO | T2O | Processing of RTGS standing orders | 15 mins | 04 February 2023 11:40 | 04 February 2023 11:55 | 241 | 243 | Active
242 | MWCP7 | ALL | MWCP7 - T2O Confirm RESO and CBs start reconciliation of SO | 10 mins | 04 February 2023 11:55 | 04 February 2023 12:05 | 242 | 245,246,247,248,249,250,251,252,253,254,255,256,257,258,259,260,261,262,263,264,265,266,267,268,269 | Active
269 | MWCP8 | ALL | MWCP8 - CBs give Green Light for T2Ps | 10 mins | 04 February 2023 13:05 | 04 February 2023 13:15 | 245,246,247,248,249,250,251,252,253,254,255,256,257,258,259,260,261,262,263,264,265,266,267,268,269 | 271 | Active
270 | T2.MW.CB.T2PGL | ALL CBs | CBs give green light to T2Ps | 10 mins | 04 February 2023 13:15 | 04 February 2023 13:25 | 270 | 273,274,275,276,277,278,279,280,281,282,283,284,285,286,287,288,289,290,291,292,293,294,295,296,297,298,299,348,300,324,301,325,302,326,303,327,304,328,329,306,330,307,331,308,332,309,333,310,334,311,335,312,336,313,337,314,338,315,339,316,340,317,341,... | Active
272 | T2.MW.T2P.BAL.REC | ALL T2Ps | T2P balance reconciliation (optional) | 245 mins | 04 February 2023 13:25 | 04 February 2023 17:30 | 271 |  | Active
292 | T2.MW.T2P.BAL.REC | NL-T2Ps | T2P balance reconciliation (optional) | 245 mins | 04 February 2023 13:25 | 04 February 2023 17:30 | 271 |  | Active
317 | T2.MW.T2P.SO.REC | NL-T2Ps | T2P standing orders reconciliation (conditional and optional) | 245 mins | 04 February 2023 13:25 | 04 February 2023 17:30 | 271 |  | Active
342 | T2.MW.T2P.LT | NL-T2Ps | T2P liquidity transfers (optional) | 245 mins | 04 February 2023 13:25 | 04 February 2023 17:30 | 271 | 349 | Active
348 | MWCP9 | ALL | MWCP9 - End of the MWP – Green Light for T2S NTS | 10 mins | 04 February 2023 17:30 | 04 February 2023 17:40 | 324,325,326,327,328,329,330,331,332,333,334,335,336,337,338,339,340,341,342,343,344,345,346,347,348 | 350 | Active
349 | T2.MW.T2O.T2SNTS | T2O | Start of T2S NTS | 200 mins | 04 February 2023 17:40 | 04 February 2023 21:00 | 349 | 351 | Active
350 | T2.MW.T2O.MW | T2O | Maintenance Window | 660 mins | 04 February 2023 21:00 | 05 February 2023 08:00 | 350 | 352 | Active
351 | T2.MW.T2O.RTSII | T2O | Start of RTGS RTS II | 0 mins | 05 February 2023 08:00 | 05 February 2023 08:00 | 351 | 353 | Active
352 | T2.MW.T2O.PVW | ALL T2Ps | Start of Payment validation window | 120 mins | 05 February 2023 08:00 | 05 February 2023 10:00 | 352 | 354 | Active
356 | T2.MW.T2.A2A.U2A.CLO | T2O | A2A and U2A channels closed for CLM/RTGS | 0 mins | 05 February 2023 10:00 | 05 February 2023 10:00 | 352 | 353 | Active
353 | T2.MW.T2O.PVW.LLI | T2O | Operator intervention for payments blocked by incorrect DN or PTA | 120 mins | 05 February 2023 10:00 | 05 February 2023 12:00 | 356 | 357 | Active
357 | T2.MW.T2.A2A.U2A.OPN | T2O | A2A and U2A channels opened for CLM/RTGS | 0 mins | 05 February 2023 12:00 | 05 February 2023 12:00 | 353 | 358 | Active
358 | T2.MW.MMCALL | ALL | Migration managers call to confirm completion of post-migration activities | 15 mins | 05 February 2023 12:00 | 05 February 2023 12:15 | 357 |  | Active