## Version + Abbr.
Version 1.0 | 2025-03-21
Abbreviations |  | Short description
BT | Blue Team | This TIBER QA Checklist has been derived from the TIBER EU Framework.
BTTR | Blue Team Test Report | Applicable to both TLPT and TIBER testing.
CIF | Critical or Important Function | It is to support the CTL in planning all activities and deliverables in the right order,
CSP | Critical Service Provider | which contributes to the quality assurance of the overall test.
CT | Control Team
CTL | Control Team Lead
CTI | Cyber Threat Intelligence
DORA | Digital Operational Resilience Act
ESCB | European System of Central Banks
GTL | Generic Threat Landscape
HUMINT | Human Intelligence
ICT | Information and Communication Technology
OSINT | Open-Source Intelligence
PT | Purple Teaming
RTT | Red Team Testers
RTTP | Red Team Test Plan
RTTR | Red Team Test Report
TCT | TIBER Cyber Team
TIBER | Threat Intelligence-Based Ethical Red Teaming
TIP | Threat Intelligence Provider
TKC | TIBER-EU Knowledge Centre
TLPT | Threat Led Penetration Testing
TSR | Test Summary Report
TI | Threat Intelligence
TTIR | Targeted Threat Intelligence Report
TM | Test Manager
TTP | Tactics, Techniques and Procedures

## Preparation
Preparation phase: notification + initiation + scoping + procurement (6 months)
Actions and description | Responsible | Status | Deliverables | Guidance
Notification (Month 0)
Send written notification mail | The TIBER authority | Not started | • Written notification mail | Note: The TCT is strongly encouraged to contact the entity as early as possible, ideally before the written notification. • The TIBER authority is responsible for sending it • Keeping in mind the confidentiality of the test • Indicates the start of the preperation phase, which means the start of the test • The preparation phase lasts no longer than six months from the start date high lighted in the notification.
Assign a Test Manager (TM) | TCT | Not started | • Assigned TM
Plan the notification meeting | TM | Not started | • Notification meeting In the notification meeting the TM will brief the entity on: - its designation to carry out a mandatory or voluntary test - the stakeholder roles and responsibilities - the testing process'its elements and deliverables - the TCT and CT composition | • This meeting is to discuss and coordinate when the test will start, also keeping in mind a lengthy procurement and scoping process. • Moreover the entity needs to anticipate potential resource and budget constraints. Participants to the notification meeting are at least the entity representatives and the TM.
Identify other authorities or entities which might be included in the test. | TM | Not started | • Identified other authorities or entities | • The TM briefs all parties involved on the steps in the TIBER-EU process, documenation, stakeholder roles and responsibilities.
Inform all other relevant legal parties to be included in the test | CTL | Not started | • Informed other relevant legal parties | • For example CSP's
Initiation (month 1 - month 3)
Prepare a (project) initiation document and determine code name | CTL | Not started | • Draft initiation document Note: the document is based on: TIBER-EU Initiation Documents Guidance | • The initiation document which include an project charter - compromising a high level plan - and communication details and channels to be established • The initiation document should be delivered to the TM no later than three months after the written notification is received. • The initiation document will be subsequently assessed and validated by the TM.
Finalise the initiation document | CTL | Not started | • Final initiation document | The final initiation document include the project charter, including: • a high level project plan • a (separate) risk log to be managed (to be updated throughout the test) • the name and contact details of the CTL • information on the intended use of internal and/or external RTT • secure communication and data transfer channels • the code name of the test • any CIFs the entity operates or shares in another Member State • any CIFs supported bij ICT third party service providers
Set up the CT | CTL | Not started | • Control Team (CT) | • The CT compromises a select number of individuals who have critical decision-making capacity and/or experts (see TIBER-EU Framework)
Plan and host the initiation meeting | CTL | Not started | • Initiation meeting In the initiation meeting the envisioned CTL should brief the TM on: - the content of the (project) initiation document - the planned composition of the CT - contractual considerations about procurement - initial efforts undertaken to manage the risks of the test.
Scoping (month 3 - month 6)
Draft the TIBER-EU Scope Specification Document (SSD) | CTL | Not started | • Draft Scope Specification Document (SSD) Note: the document is based on: TIBER-EU Scope Specification Document Guidance | • The TCT validates the SSD and informs the CTL about the validation. • Once contracted, the CT will share the SSD with the TIP and RTT and ask for feedback.
Give feedback and make sure the feedback is processed before the scoping meeting. | TCT | Not started | • Updated draft Scope Specification Document (SSD)
Plan and host the scoping meeting | CTL | Not started | • Scoping meeting Note: the scoping meeting takes place after the initiation meeting but no later than six months after the written notification is received. | In the scoping meeting the CT, TCT an TM (and TIP/RTT if already procured) should: • Discuss the scope of the test, including feedback from the TCT and/or supervisor (where applicable) • Update the TIP and RTT on the scope (this might be done afterwards if the providers are not yet procured) • Present the updated risk management measures and documentation (risk log). • Discuss the flags (at least one for each system in scope)
Process feedback and finalise the Scope Specifcation Document (SSD) | CTL | Not started | Final Scope Specification Document (SSD) | • Feedback from the TCT, TIP and RTT (after procurement) processed
The SSD should be approved by the management body of the entity and delivered to the TM | CTL | Not started | Final Scope Specification Document (SSD) approved by the management body of the entity | • Delivered to the TM within six months after receiving the written notification
Procurement (month 3 - month 6)
Prepare and send out a Request for Proposal (RfP) in line with the TIBER EU framework and based upon discussions during the notification, initiation and scoping phases. | CTL | Not started | • RfP based on the TIBER EU Guidance for Service Provider Procurement (GSSP) | • The CTL is responsible for the entire procurement process and needs to involve all necessary parties within the organisation (Legal, Purchasing, etc) • The CTL needs to make sure - for test secrecy purposes - that the list of people involved is not bigger than strictly nessesary • The requirements for providers can be found in the GSSP • The RFP should explicitly mention when the TI / RT / GT phases roughly take place
The TCT may review the CVs of threat intelligence analysts and red team operators. | TCT | Not started | • Sent CV's (not anonimized) if applicable. In case of a new provider or new team (members). | • The TCT assesses whether the requirements for testers for the carrying out of TLPTs under DORA regulation, DORA RTS for TLPT, and TIBER-EU procurement guidelines are met. • The TCT wil assess the CV's and see if they meet the procurement guidelines. • The TCT will align with the CTL on the assessment.
Sign contract with RTP and/or TIP | CTL | Not started | • Signed contract | • The CTL is responsible for the contract between the organisation and the involved providers
Update initiation documentens including the project plan | CTL | Not started | • Updated initiation document | • Update is in consultation with the TM • The final schedule of process steps, deliverables and meetings • Secure communication and data exchange • Code name is shared with all relevant stakeholders
Plan and host the launch meeting | CTL | Not started | • Launch meeting planned (after signing the contract) Note: the launch meeting takes place no later than six months after the written notification is received. | • This is officially last step of the preparation phase (therefor the the first step of the test phase) • All relevant stakeholders are invited at least the TM, CT, TIP/RTT) • The TIP/RTT are officially onboarded • The CT composition and project plan are presented • Presentation of the scope (SSD), if feasible • The test process, rule of engagement, secure communication channels are presented • All stakeholders discuss and explain their expectations and cooperation • Pro-actively schedule and alighn on weekly meetings for the next phase to be launched.
Formally launch of the test phase | CTL | Not started | • Formal GO from the TCT | • The TCT can give a formal GO for starting the Test phase, after: - the test process, rule of engagement, secure communication channels have been presented - the scoping document (incl. C-level) has been approved - the TCT and CT composition are presented and explained - roles and responsibilities are clearly aligned between TM, CT, TIP and RTT

## Threat Intelligence
Test phase - Threat Intelligence (4-6 weeks)
Actions and description | Responsible | Status | Deliverables | Guidance
TI Collection
Plan weekly meetings during the test phase | CTL | Not started | • Weekly progress meetings • Meeting minutes (containing at least actions planned & decisions) | • Indicates the start of the TI phase, which means the start of the test • TCT, CT, TIP and RTT will be invited
Organise communication and document sharing channels | CTL | Not started | • A communication channel for messages • A communication channel for documents | • The CTL should set up channels through which can be communicated during the test • This includes a messaging service such as Wired or Signal and a data transfer platform such as Tresorit or MSafe
Sharing relevant data and documentation with the TIP | CTL | Not started | • N/A | • The CTL shares all information necessary with the TIP for a succesful progression of the TI phase. This includes: • The scoping document (SSD) • The GTL (if produced by the respective jurisdiction) • Old TI reports (if desired by the TIP) • Information or documentation on the organisation (if applicable and desired by the TIP) • the current threat assessment and/or threat register • examples of recent attacks on the entity or its environment
Plan and host a business overview workshop | CTL | Not started | • Business overview workshop | • The CTL organises a business overview workshop for the TIP • This workshop should be facilitated by someone in the entity that knows the relevant processes, systems, data and people that are important for the business side of the organisation • The workshop will help the TIP to get a better understanding of the value of the critical processes, specific data and systems (crown juwels) making the entity unique as described in the scoping document • If deemed useful, the RTP can be invited to this workshop too.
Gathering of threat intelligence | TIP | Not started | • N/A | • The (internal or external) TIP starts the process of threat intelligence gathering. • The Threat Intelligence Report Guidance can be used during the TI-process and creation of the TI report.
Delivery and discussion of the draft Targeted Threat Intel Report (TTIR) | TIP | Not started | • Draft version of TTIR | • Although not a hard requirement in the framework, it is advisable to share a draft version of the TTI-report with the TCT after ca. three weeks • The TCT will check whether it meets the requirements and will provide extensive feedback on the draft report once
Scenario creation
Create a broad set of threat led scenarios | TIP | Not started | • Attack scenarios, includin at least one non-threat-led scenario. | • The Threat Intelligence Report Guidance can be used during the TI-process and creation of scenarios. • Scenarios should be based on intel aquired during the target identifications process. • Scenarios should present a credible picture of the entity's cyber threat landscape.
Plan the scenario selection meeting | CTL | Not started | • Scenario selection meeting planned | • TCT, CT, TIP and RTT will be invited • Participation of C-level is optional in this meeting • After the meeting the C-level must be informed about selected scenarios which is adviced to increase awareness on board level.. • After the meeting three scenarios must have been selected. • A maximium of one scenario may be non-threat-led
Host the scenario selection meeting | CTL | Not started | • Scenarios explained and selected | • The TIP introduces a broad set of realistic attack scenarios. • Selection is done, based on: - Recommendation of the TIP - Input provided by the TCT - Feasibility of the proposed scenarios for execution, based on the expert judgement of the RTT - strategioc criteria (e.g. regarding scenarios of past tests, the need for leg-ups) - the size of the overall risk profile of the entity.
Finalise the TTI report | TIP | Not started | • Final Targeted Threat Intel report | • The RTT will be more involved • If the draft TTI report is on the right track, the CTL can ask the RTP to start drafting the Red Team Test Plan (RTTP). This will make the transition from TIP to RTT smoother and the entire process more time efficient • RTT is encouraged to give feedback during the final stage of the TTI proces to enrich the the TTIR.
Update the risk management controls if applicable | CTL | Not started | • Updated risk management log and controls
Send the final draft TTIR to the TM for approval | CTL | Not started | • Final draft and to be approved TTIR
Plan and host the TTIR meeting | CTL | Not started | In this meeting the TIP should present: • the collected TTI • the selected and elaborated scenarios for testing in detail • the final draft TTIR | • The TIP delivers a dedicated TTIR, containing the elements as described in the TIBER-EU Threat Intelligence Report Guidance. • During this meeting with the TM, CT, RTT and TIP, all parties agree that the test will go ahead using the TTI report and scenarios as produced by the TIP • During this meeting, the TIP will run the other participants through its work process and conclusions • This meeting may be combined with the Red Team Test Plan (RTTP) meeting (next tab: Ted Teaming) • The TTIR must be formally approved after the meeting by the TM • It is up to the CTL to share the TTIR with the C-level sponsor for formal approval in writing. For example by email.
Go/No Go on TTI report and chosen scenario(s) | TM | Not started | • TTI Report with TI based scenarios completed and agreed upon

## Red Teaming
Test phase - Red Teaming (minimal 14-15 weeks)
Actions and description | Responsible | Status | Deliverables | Guidance
RT Test Plan (RTTP) creation (2-3 weeks)
(Continue) drafting the RT Test Plan | RTT | Not started | • Draft RTTP | • The RTT develops and integrates the attack scenarios into an RTTP, leveraging on the secenarios included in the TTIR • For guidance on the RTTP attack plan, refer to the Red Team Test Plan Guidance • The RTP may share a draft version of the plan with the CTL and TCT to ensure everyone is aligned and any desired changes can be incorporated
Preparing potential leg ups (being part of the RTTP) | RTT | Not started | • N/A | • As the RTTP is getting shape, the RTT and CTL can more precisely prepare leg ups, based on the work done in earlier phases of the test • Expected leg ups should be mentioned in the RTTP planning
Update the risk management controls if applicable | CTL | Not started | • Updated risk management log and controls
Plan and host the RT Test Plan (RTTP) meeting | CTL | Not started | • Formal Go for starting active RT testing | Please check the guidance TIBER-EU 2.0 Framework regarding the RTTP meeting, stating at least the following: • A meeting is being organised by the CTL where at least the TM, the CTL and RTT are present. C-level sponsor is advised to participate and must be informed about what scenarios are taking place and which live production systems are targeted • During this meeting, the RTT presents the RT Test Plan and discusses risk management strategies. Any outstanding questions will be adressed • The C-level gives a formal go or no go in writing. Active RT testing cannot start without this approval • After the meeting, the Go-decision needs to be formalised in writing via email from the C-level to the TM • To save time, the formal approval from C-level of the TTI Report and RT Test Plan can be combined in one meeting and/or email • It is up to the CTL to share the TTIR and RTTP with the C-level sponsor for approval
Organise weekly meetings during RT phase | CTL | Not started | • Weekly progress meetings | • The CTL should organise and chair weekly meetings as defined in the RT Test Plan • During these weekly (mostly 30 minute) online meetings, the RTT informs all involved parties about the progress of the RT phase, per scenario: - actions done past week - current position (foothold), consider and agree on possible next steps - actions planned and summarised for the upcoming week - deviations from the RTTP and amendments in the flags, objectives and emulations of TTPs - expected leg ups and impact - potential risks and mitigations - planning status • The TIP may be involved for consultation if requested by the CTL • The CTL keeps a log of all important decisions made during these meetings • The RTP shares the updates at least one day in advance so that all participants can prepare for the meeting.
Active RT testing (minimal 12 weeks)
Execution of active RT testing | RTT | Not started | • N/A | • After TCT and CT have approved the RT Test Plan, the RTT starts preparation followed by executing the planned scenario's (TTP's) as described in the RT Test Plan • The RTT provides a documented update one day before the weekly meetings
Set up 'Out plan' for each scenario if applicable | RTT | Not started | • Out plan, however not mandatory, it is important to stay in control and sit together with the RTT, CTL and TM to align and agree on the details before starting the out phase. | • As the RT-phase progresses, the RTT must align and agree on the details of the out phase, such as: - suitable date, start time and duration of data exfiltration - amount of (dummy) data, how to store it, how to deal with exfiltrated data - how much money to transfer, to which bank account, impact of it - potential risks to be mitigated - how to communicate - escalation paths - when to disclose the test • It does not have to be recorded in a formal document, but the RTP must demonstrate that it is in control during the entire out phase
The current position may be demonstrated and the'Out plan' presented to the CT incl. C-level | RTT | Not started | • Demonstration of the current position and presentation of the Out plan. | • Not mandatory, however adviced to increase awareness on board level.
Define concrete end of active RT testing and finish the RT phase | CTL | Not started | • Technical restoration procedures | • The CTL informs the BT that the RT test was conducted and ended • Technical restoration procedures are planned and coordinated with the CT and BT, and ideally not occur before the replay and PT in the Closure phase • Technical restoration procedures should include: - command and control deactivation - scope and date kill switches - removal of backdoors and other malware - potential breach notification - procedures for future back-up restoration which may contain malware or tools installed during the test - monitoring of the BT activities and information to the CT of any possible detections

## Closure phase
Closure phase (18 weeks)
Actions and description | Responsible | Status | Deliverables | Guidance
RT Test Report (4 weeks)
RT Test Report (RTTR) | RTT | Not started | • RT Test Report (RTTR) | • The reports must comply to the available guidance in the DORA RTS for TLPT and TIBER EU framework guidance documents. • The draft RT Test Report must be shared by the RTT within four weeks after ending the RT phase • The RTTR must comply to the available TIBER EU Red Team Test Report Guidance
BT Test Report, Replay + PT exercise (6 weeks)
Blue Team Test Report (BTTR) | CTL | Not started | • BT Test Report (BTTR) | • The reports must comply to the available guidance in the DORA RTS for TLPT and TIBER EU framework guidance documents. • The RTTR is input for the BTTR • The draft BTTR must be produced by the BT no later than ten weeks after ending the active RT phase • The BTTR should be drafted ahead of the replay and PT exercises • The BTTR must comply to the available TIBER EU Blue Team Test Report Guidance
Replay
Plan and host the meeting : replay exercise Tip! Merge this meeting with the next step 'meeting: Purple Team exercise' | CTL | Not started | • Meeting with at least CT, BT, RTT and TM (if feasible) After delivery of the RTTR and BTTR | • The RTT and the BT go through the tested scenarios step by step following the timeline as described in the RTTR and BTTR • They discuss: - the progression through the attack stages of each scenario and relevant learnings generated - what else could have been achieved by the RTT with more time and resouces - potential remediation measures - general questions from the BT
Purple Teaming
Plan and host the meeting : Purple Team exercise, Closely after or together with the replay exercise | CTL | Not started | • Meeting with at least CT, BT, RTT After delivery of the RTTR and BTTR • Available guidance: TIBER-EU Purple team Guidance | • The Purple Team exercise is preferably planned physically, in-person • The RTT and BT discuss all remaining or additional topics relevant to the CT and the BT, such as: - relevant issues that could not be tested during the active RT phase - particular vulnerabilities identified during the test - other steps which could have been taken by the RTT and potential BT responses - alternative scenarios and their potential consequences - proof of concepts - discussion of anticipated remediation measurees with the RTT - business continuity exercises
Test Summary Report + 360 Feedback Report + Remediation Plan (8 weeks)
Test Summary Report
Deliver the Test Summary Report (TSR) | CTL | Not started | • Final TSR Eight weeks after the TM has sent out a notification of the completed assessment of the RTTR and BTTR | • The findings and learnings of the replay and PT exercises will feed directly into the final TSR • It must comply to the available guidance: TIBER-EU Test Summary Report Guidance
360 Feedback
Plan and host the 360 feedback meeting | TM | Not started | • Meeting with at least CT, BT, RTT, TIP and TM Before the TM approval of the TSR and remediation plan | • After completion of the replay and PT exercises • All participants should deliver and receive their written feedback to the TM • The TM, CTL, RTT an TIP (leads) and BT lead participate and deliver feedback on eachother and on the ovrall (testing) process as well as the TIBER-EU framework • The TM participates but is not obliged to provide feedback
Remediation plan
Deliver the Remediation plan | CTL | Not started | • Remediation plan Eight weeks after the TM has sent out a notification of the completed assessment of the RTTR and BTTR | • The findings and learnings of the replay and PT exercises will feed directly into the Remediation Plan • It must comply to the available guidance: TIBER-EU Remediation Plan Guidance
Attestation
Sign and share the Attestation document | TCT | Not started | • Signed Attestation document shared After the TSR and the Remediation plan have been agreed upon | • If the test has been conducted in accordance to the TIBER-EU framework, the TCT will sign and share the Attestation document • It must comply to the available guidance: TIBER-EU Attestation Guidance

## Dropdown (hidden)
Status | Threat Intelligence | Red teaming | Purple teaming | Gold teaming
Not applicable | T1 - Internal TI team / GTL | R1 - One scenario, assumed compromise | P1 - PT fundamentals | G1 - Walkthrough
Not started | T2 - Internal TI team / GTL + old TI report | R2 - One scenario, in-through-out | P2 - PT full | G2 - Tabletop exercise
In progress | T3 - RTP provides limited TI report | R3 - Two scenarios, assumed compromise |  | G3 - Simulation without counterplay
Done | T4 - TIP provides full TI report | R4 - Two scenarios, one assumed compromise, one in-through-out |  | G4 - Simulation with counterplay
|  | R5 - Two scenarios, in-through-out |  | G0 - Not applicable
R6 - Three scenarios, including scenario X
R7 - Custom built