## Dashboard
TLPT and TIBER Quality Assurance Checklist for TIBER-EU
• This format for the TIBER-EU Quality Assurance Checklist is intended for use by the Control Team Lead to keep track of progress during an TIBER/TLPT test and to determine whether all required steps have been completed and deliverables are delivered and is based on the TIBER-EU framework (published 2025). • The Control Team Lead is responsible for filling out the Quality Assurance Checklist. • Disclaimer: This document can be used optionally and serves as a guiding checklist, but should not be construed as legal advice. The TIBER-EU framework and its underlying guides should always be used as reference when conducting a TIBER test.
Code name of the test
Year
| Phase | Completed?
| Preparation | No
| Threat Intelligence | No
| Red Teaming | No
| Closure | No
| Attestation | No
| Test complete? | No

## Preparation
Preparation phase: notification + initiation + scoping + procurement (6 months)
Actions and description | Responsible | Status | Deliverables | Guidance
Notification (Month 0)
Send written notification email | TM | Not started | • Written notification mail | Only applicable for DORA TLPT
CTL and TM discuss contractual topics and agree on high level test planning. | TM | Not started | • Signed contract between TCT-DNB and FI | Only applicable for voluntary TIBER
Plan and host the notification meeting | TM | Not started | • Notification meeting | • In the notification meeting the TM will brief the entity on: - its designation to carry out a mandatory or voluntary test - the stakeholder roles and responsibilities - the testing process'its elements and deliverables - the TCT and CT composition • Moreover the entity needs to anticipate potential resource and budget constraints. • Participants to the notification meeting are at least the entity representatives and the TM. For DORA TLPT this meeting follows shortly after the formal notification For voluntary TIBER tests, this meeting is the first formal meeting after having one or more informal meetings where the high level planning of the exercise was discussed and the contract between the TCT and the FI has been signed.
Identify other authorities or entities which might be included in the test. | TM | Not started | • Identified other authorities or entities to be included in the CT and/or their role as participating/observing TCT. | • The TM briefs all parties involved on the steps in the TIBER-EU process, documenation, stakeholder roles and responsibilities.
Inform all other relevant legal parties to be included in the test | CTL | Not started | • Informed other relevant legal parties and/or ICT TPSPs | • For example ICT TPSPs
Initiation (month 1 - month 3)
Prepare a (project) initiation document and determine code name | CTL | Not started | • Draft initiation document(s) Note: the required content of these document(s) is based on: TIBER-EU Initiation Documents Guidance | • The initiation document which include an project charter - compromising a high level plan - and communication details and channels to be established • The initiation document should be delivered to the TM no later than three months after the written notification is received. • The initiation document will be subsequently assessed and validated by the TM.
Finalise the initiation document | CTL | Not started | • Final initiation document | The final initiation document include the project charter, including: • a high level project plan, including the envisioned deadlines of the preparation, testing and closure phase, as well as the deadline for the remediation plan • the name and contact details of the CTL • information on the intended use of internal and/or external RTT • secure communication and data transfer channels • the code name of the test • any CIFs the entity operates or shares in another Member State • any CIFs supported bij ICT third party service providers
Set up the CT | CTL | Not started | • Control Team (CT) | • The CT compromises a select number of individuals who have critical decision-making capacity and/or experts (see TIBER-EU Control Team Guidance) • The CTL makes sure that the CT is aware of the test, the need for secrecy and the process the CT should go through in case the BT detects and escalates a test-related incident. • The following functions or types of personnel should be part of the CT: - Control team lead (a backup is recommended); - subject Matter Experts (SMEs); - C-Level Member. C-level members are usually included in the CT in an extended composition; - other needed expertise, e.g. project manager; - relevant third-party provider(s).
Inform the TM of the setup of the CT for validation | CTL | Not started | • Validated Control Team (CT) | • The TM validates the initial composition of the CT, as well as any subsequent changes to it. and informs the entity of its validation.
Organise communication and document sharing channels | CTL | Not started | • A communication channel for messages • A communication channel for documents | • The CTL should set up channels through which can be communicated during the test • This includes a secure messaging service such as Signal and a data transfer platform such Msafe
Undertake initial efforts to manage the risks of the test | CTL | Not started | • An intial risk log | • Since testing is conducted on live production systems, the CT should establish comprehensive risk management measures during the preparation phase to address all potential risks arising from the conduct of the test. • The risk log needs to be managed and updated throughout the test • More information on risk management can be found in chapter 4 of the TIBER-EU framework.
Plan and host the initiation meeting | CTL | Not started | • Initiation meeting | • In the initiation meeting the envisioned CTL should brief the TM on: - the content of the (project) initiation documents - the planned composition of the CT - contractual considerations regarding procurement - initial efforts undertaken to manage the risks of the test. • The intiation meeting takes place no later than three months after the notification (TLPT) or the contractual startdate of the test (TIBER). • Participants to this meeting al at least: the entity representatives and the TM.
Validation of the initiation documents | TM | Not started | • Validated Initiation Documents | • The initiation documents will be presented by the CTL in the initiation meeting and are subsequently assessed and validated by the TM.
Scoping (month 3 - month 6)
Draft the TIBER-EU Scope Specification Document (SSD) | CTL | Not started | • Draft Scope Specification Document (SSD) | • The SSD is based on: TIBER-EU Scope Specification Document Guidance • During the drafting process the CTL can consult the TM for intermediate feedback. • Once contracted, the CT will also share the SSD with the TIP and RTT and ask for feedback. • Delivered to the TM within six months after receiving the written notification
Process feedback and prepare final draft version of the Scope Specifcation Document (SSD) | CTL | Not started | • Final Scope Specification Document (SSD) | • Feedback from the TLPT authority, TIP and RTT (if already procured) processed
Validation of the SSD | TM | Not started | • Validated Scope Specification Document (SSD) | • The TM (on behalf of the TIBER or TLPT authority) validates the SSD and informs the CTL about the validation.
Approval of the SSD by the management body of the entity and delivered to the TM | CTL | Not started | • Approved Scope Specification Document (SSD) | • The CT will deliver a SSD, setting out: - the CIFs identified by the entity - for each CIF in scope of the test: * the reason why the CIF is included * the ICT sytem(s) supporting the CIF * if identified CIFs are not included in the scope of the test, the CT should provide an explanation of why the CIFs are not included in the scope
Update the risk management controls when applicable | CTL | Not started | • Updated risk management log and controls | • The risk log needs to be managed and updated throughout the test • More information on risk management can be found in chapter 4 of the TIBER-EU framework.
Plan and host the scoping meeting | CTL | Not started | • Scoping meeting | • The scoping meeting takes place after the initiation meeting but no later than six months after the written notification is received. • In the scoping meeting the CT, TCT an TM (and TIP/RTT if already procured) should: - Discuss the scope of the test, including feedback from the TCT and/or supervisor (where applicable) - Update the TIP and RTT on the scope (this might be done afterwards if the providers are not yet procured) - Present the updated risk management measures and documentation • Participants to this meeting are: the CTL, CT, TM, (TIP and RTT)
Procurement (month 3 - month 6)
Prepare and send out a Request for Proposal (RfP) in line with the TIBER EU framework and based upon discussions during the notification, initiation and scoping activities | CTL | Not started | • RfP based on the TIBER-EU Guidance for Service Provider Procurement | • The CTL is responsible for the entire procurement process and needs to involve all necessary parties within the organisation (Legal, Purchasing, etc) • The CTL needs to make sure - for test secrecy purposes - that the list of people involved is not bigger than strictly nessesary • The RFP should explicitly mention when the testing phase roughly should take place
Assess compliance of the TI and RT resources and document assessment | CTL | Not started | • Evidence of assessment of the compliance of the resources • Send CV's (not anonimized) if applicable. In case of a new provider or new team (members). | • The CT should document its assessment of compliance of the provider resources for TI and RT with the TIBER-EU Guidance for Service Provider Procurement and provide evidence of compliance to the TM. • The CT does not proceed with contracting the selected TIP/RTP whre the TM assesses that the selected providers do not ensure compliance
The TM assesses the CT's assessment of the CVs of the TI and RT resources | TM | Not started | • Feedback and (non) objection for completion of the procument | • The TM assesses that the selected providers and their resources are compliant with the requirements in the TIBER-EU Guidelines for Service Provider Procurement • The TM will provide the CT with their feedback of the assessement
Sign contract with RTP and/or TIP | CTL | Not started | • Signed contract | • The CTL is responsible for the contract between the organisation and the involved providers
Update initiation documents including the project plan | CTL | Not started | • Updated initiation document | • Update is in consultation with the TM • The final schedule of process steps, deliverables and meetings • Secure communication and data exchange • Code name is shared with all relevant stakeholders
Update the risk management controls when applicable | CTL | Not started | • Updated risk management log and controls | • The risk log needs to be managed and updated throughout the test • More information on risk management can be found in chapter 4 of the TIBER-EU framework.
Plan and host the launch meeting | CTL | Not started | • Launch meeting | • During the launch meeting, the following actions are performed: - the TIP/RTT are officially onboarded - the CT composition and project plan are presented - the presentation of the scope (SSD), if feasible - the test process, rule of engagement, and established communication details and channels are presented - all stakeholders discuss their expectations and cooperation • Participants to this meeting are: the CTL, CT, TM, TIP and RTT • The launch meeting is held when the procurement is finalised, no later than six months after the written notification. The meeting concludes the preparation phase.
Total preparation phase |  | Incomplete

## Threat Intelligence
Test phase - Threat Intelligence (4-6 weeks)
Actions and description | Responsible | Status | Deliverables | Guidance
TI Collection
Plan weekly meetings during the test phase | CTL | Not started | • Weekly progress meetings • Meeting minutes (containing at least actions planned & decisions) | • Indicates the start of the TI activities in the testing phase • TCT, CT, TIP and RTT will be invited
Sharing relevant data and documentation with the TIP | CTL | Not started | • N/A | • The CTL shares all information necessary with the TIP for a succesful progression of the TI phase. This includes: - the scoping document (SSD) - the GTL (if produced by the respective jurisdiction) - old TI reports (if desired by the TIP) - information or documentation on the organisation (if applicable and desired by the TIP) - the current threat assessment and/or threat register - examples of recent attacks on the entity or its environment
(Optional) Plan and host a business overview workshop | CTL | Not started | • (Optional) Business overview workshop | • The CTL optionally organises a business overview workshop for the TIP (if deemed necessary) • This workshop should be facilitated by someone in the entity that knows the relevant processes, systems, data and people that are important for the business side of the organisation • The workshop will help the TIP to get a better understanding of the value of the critical processes, specific data and systems (crown juwels) making the entity unique as described in the scoping document • If deemed useful, the RTP can be invited to this workshop too.
Gathering of threat intelligence | TIP | Not started | • presentation of the ongoing outcomes of the threat intelligence activities during the weekly meetings | • The TIP starts the process of threat intelligence gathering. • The Threat Intelligence Report Guidance can be used during the TI-process and creation of the TI report.
Delivery and discussion of the draft Targeted Threat Intel Report (TTIR) | TIP | Not started | • Draft version of TTIR | • Although not a hard requirement in the framework, it is advisable to share a draft version of the TTI-report with the TCT after ca. three weeks • The TCT will check whether it meets the requirements and will provide extensive feedback on the draft report once
Scenario and targetted threat intelligence report (TTIR) creation
Draft the TTIR | TIP | Not started | • Draft TTIR | • The TIP shares the draft TTIR with the CT and TCT for feedback. • Feedback from the TCT can be expected on the setup of the report and the content. Therefor, it is adviced to share a 0.5 version of the report for initial guidance on the setup and draft content. After that the 0.8 version can be shared for a content-based review by the TCT before sharing the final draft version for the TTIR meeting.
Create a broad set of threat led scenarios | TIP | Not started | • The long list of attack scenarios, based on the intelligence acquired and that are threat intelligence based and specifically tailored to the entity's business enviroment. | • The Threat Intelligence Report Guidance can be used during the TI-process and creation of scenarios. • Scenarios should be based on intel aquired during the target identifications process. • Scenarios should present a credible picture of the entity's cyber threat landscape.
Plan and host the scenario selection meeting | CTL | Not started | • Scenario selection meeting | • The CTL selects/adapts three or more scenarios to be followed during testing, based on: - the recommendation of the TIP, taking into account the threat-led nature of the scenarios - the input provided by the TM - the feasibility of the proposed scenarios for execution, based on the expert judgement of the RTT - strategic criteria (e.g. regarding scenarios of past tests, the need for leg-ups) - the size, complexibility and overall overall risk profile of the entity and the nature, scale and complexity of its services, activities and operations. • Participants to this meeting are the CT, TCT, TIP and RTT • Participation of C-level is optional in this meeting • After the meeting the C-level must be informed about selected scenarios which is adviced to increase awareness on board level.. • After the meeting three scenarios must have been selected. • A maximium of one scenario may be non-threat-led (scenario X).
Prepare the final draft of the TTIR | TIP | Not started | • Final draft TTI report | • The TIP delivers a dedicated TTIR, containing the elements as described in the TIBER-EU Guidance for the TTI report, containing at least: - the overall scope of the intelligence research - an overall assessment of what concrete, actionable intelligence can be found about the entity - threat intelligence analysis considering the general threat landscape and particular situation of the entity - threat profiles of malicious actors that may target the entity - threat scenarios: at least 3 end-to-end threat scenarios for the threat profiles • The RTT will be more involved • If the draft TTI report is on the right track, the CTL can ask the RTP to start drafting the Red Team Test Plan (RTTP). This will make the transition from TIP to RTT smoother and the entire process more time efficient • RTT is encouraged to give feedback during the final stage of the TTI proces to enrich the the TTIR.
Plan and host the TTIR meeting | CTL | Not started | • TTIR meeting | • In this meeting the TIP should present: - the collected target intelligence - the selected and elaborated scenarios for testing in detail - the final draft TTIR
TTIR approval | CTL | Not started | • Approved TTIR | • The TTIR must be formally approved by the TM and the CT (including the C-level representative) • The CTL should send the TTIR tot the TM for approval, who will notify the CTL accordingly.
Update the risk management controls when applicable | CTL | Not started | • Updated risk management log and controls | • The risk log needs to be managed and updated throughout the test • More information on risk management can be found in chapter 4 of the TIBER-EU framework.
Total threat intelligence phase |  | Incomplete

## Red Teaming
Test phase - Red Teaming (minimal 14-15 weeks)
Actions and description | Responsible | Status | Deliverables | Guidance
RT Test Plan (RTTP) creation (2-3 weeks)
Organise (at least) weekly meetings during RT phase | CTL | Not started | • Weekly progress meetings | • The CTL should organise and chair weekly update meetings for the testing phase • During these - at least - weekly (online) meetings, the RTT inform all involved parties about the progress of the RTTP drafting and during active testing, per scenario: - actions done past week - current position (foothold), consider and agree on possible next steps - actions planned and summarised for the upcoming week - deviations from the RTTP and amendments in the flags, objectives and emulations of TTPs - expected leg ups and impact - potential risks and mitigations - planning status • The TIP may be involved for consultation if requested by the CTL • The CTL keeps a log of all important decisions made during these meetings • The RTT share the update information set at least one day in advance so that all participants can prepare for the meeting.
(Optional) Arrange daily meetings and ad hoc (secure) communication involving the CT and the TM | RTT | Not started | • Ad hoc communication | • The focus of this communication should be on activities of the immediate past and short-term planned actions, expecially during critical testing activities
(Continue) drafting the RT Test Plan | RTT | Not started | • Draft RTTP | • The RTT develops and integrates the attack scenarios into an RTTP, leveraging on the secenarios included in the TTIR • For guidance on the RTTP, refer to the TIBER-EU Red Team Test Plan Guidance • The RTT may share a draft version of the plan with the CTL and TCT to ensure everyone is aligned and any desired changes can be incorporated • Expected leg ups should be mentioned in the RTTP
Preparing potential leg ups | RTT | Not started | • Prepared leg-ups | • As the RTTP is getting shape, the RTT and CTL can more precisely prepare leg ups, based on the work done in earlier phases of the test • Upon finalisation of the RTTP, the CT must prepare specific leg-ups tot the RTT, by being ready to execute all necessary processes and procedures without raising alarm and causing delay.
Update the risk management controls when applicable | CTL | Not started | • Updated risk management log and controls | • The risk log needs to be managed and updated throughout the test • More information on risk management can be found in chapter 4 of the TIBER-EU framework.
Plan and host the RTTP meeting | CTL | Not started | • Final draft RTTP | • During the RTTP meeting the RTT should present: - the planned attack steps for each end-to-end scenario, including detailed flags and expected leg-ups - time planning for each scenario - dedicated milestones - escalation contacts and procedures - rules of engagement and reporting agreements - risk management measures taken by the RTT • Participants to this meeting are at least: CT, TM, RTT, TIP (where appropriate)
RTTP approval | CTL | Not started | • Approved RTTP | • The RTTP must be formally approved by the CT (including C-level member) and TM. • Active RT testing cannot start without this approval.
Active RT testing (minimal 12 weeks)
Execution of active RT testing | RTT | Not started | • N/A | • After the RTTP is approved, the RTT start preparation and execution of the planned scenario's (TTP's) as described in the RTTP • The RTT provide the supporting documentation preferably one day prior to the update meetings
(Optional) Provide leg-ups during active testing | CTL | Not started | • Provide approved leg-ups | • The (timing of the) leg-ups must be discussed and approved by the CT and the TM before use.
(Optional) Get approval of any changes to the RTTP | RTT | Not started | • Updated approved RTTP | • Any changes to the RTTP - subsequent to its approval - must be approved by the CT and TM
Update the risk management controls when applicable | CTL | Not started | • Updated risk management log and controls | • The risk log needs to be managed and updated throughout the test • More information on risk management can be found in chapter 4 of the TIBER-EU framework. • During the active RT testing risks related to the 'out' activities can be addressed in the risk log, such as: - suitable date, start time and duration of data exfiltration - amount of (dummy) data, how to store it, how to deal with exfiltrated data - how much money to transfer, to which bank account, impact of it - other potential risks to be mitigated
Agree on concrete end of active RT testing and inform the BT that a test was conducted | CTL | Not started | • Agreement on end date of the active RT phase and uncovered test | • The CT, TIP, RTT and TM should agree on the concrete end of the active RT phase • The CTL informs the BT that the RT test was conducted and ended
Carry out technical restoration procedures | RTT and TIP | Not started | • Safeguarded integrity of the tested entity's environment | • The technical restoration procedures should be planned and coordinated with the CT and BT, and ideally not occur before the replay and PT in the closure phase • Technical restoration procedures should include: - command and control deactivation - scope and date kill switches - removal of backdoors and other malware - potential breach notification - procedures for future back-up restoration which may contain malware or tools installed during the test - monitoring of the BT activities and information to the CT of any possible detections
Total red teaming phase |  | Incomplete

## Closure
Closure phase (18 weeks)
Actions and description | Responsible | Status | Deliverables | Guidance
Red Team Test Report (RTTR), Blue Team Test Report (BTTR) creation (10 weeks), Replay and Purple Teaming
Drafting the RTTR (4 weeks) | RTT | Not started | • Final draft RTTR | • The RTT produce a RTTR, for delivery to the CT within four weeks from the end of the active red team testing phase. • The CT delivers this RTTR to the BT and the TM • The RTTR must comply to the available TIBER-EU Red Team Test Report Guidance • The RTTR should be drafted ahead of the replay and PT exercises • The TM assesses that the RTTR contains the required information and provides feedback where necessary. • Given the importance of the RTTR for the BTTR and the replay exercise, the TM is advised to provide feedback on the document once in a final stage.
Finalising the RTTR | RTT | Not started | • Final RTTR | • The provided feedback is used to finalise the RTTR. • The RTTR should include at least the following information: - Information on the performed attack - All actions that the RTT are aware of that were performed by the BT to reconstruct and attack and mitgate its effects - Discovered vulnerabilities and other findings
Drafting the BTTR (6 weeks) | CTL | Not started | • Final draft BTTR | • The BT uses the RTTR to deliver the BTTR to the CT no later than ten weeks after the end of the active red team testing phase • The CT delivers the BTTR to the RTT and the TM • The BTTR must comply to the available guidance in the TIBER-EU Blue Team Test report Guidance • The BTTR should be drafted ahead of the replay and PT exercises • The TM assesses that the BTTR contains the required information and provides feedback where necessary.
Plan and host the replay exercise | CTL | Not started | • replay exercise | • The replay exercise must take place within ten weeks after the end of the active testing • During the replay exercise, the RTT and the BT go through the actions each of the teams has taken during the test, based on the timeline of events agreed to in the reports to discuss: - the progression through the attack stages of each scenario and relevant learning generated - what else could have been achieved by the RTT with more time and resouces - potential remediation measures - general questions from the BT • Refer to: TIBER-EU Purple team Guidance • Participants to this exercise are at least: the CT, BT, RTT, TM (if feasible)
Plan and host the purple teaming exercise | CTL | Not started | • purple teaming exercise | • The purple teaming exercise must take place within ten weeks after the end of the active testing • During the purple teaming exercise, the RTT and BT discuss all remaining or additional topics relevant to the CT and the BT, such as: - relevant issues that could not be tested during the active RT phase - particular vulnerabilities identified during the test - other steps which could have been taken by the RTT and potential BT responses - alternative scenarios and their potential consequences - proof of concepts - discussion of anticipated remediation measurees with the RTT - business continuity exercises • Available guidance: TIBER-EU Purple team Guidance • Participants to this exercise are at least: the CT, BT, RTT
Finalising the BTTR | BT | Not started | • Final BTTR | • The BTTR should at least include the following elements and information: - for each attack step described by the testers in the RTTP (a) a list of detected attack actions and (b) log entries corresponding to these detections - an assesment of the findings and recommendations of the testers - evidence of the attack by the RTT collected by the BT - BT root cause analysis of successful attacks by the testers - list of lessons learned and identified potential for improvement - list op topics to be addressed in the PT exercise
Send notification of completed assessment of the RTTR and BTTR | TM | Not started | • Notification of completed RTTR and BTTR assessment | • The TM will send a notification of the completed assessment of the RTTR and BTTR to the entity
Update and/or close the risk management controls when applicable | CTL | Not started | • Updated and/or closed risk management log and controls | • The risk log needs to be managed and updated throughout the test • More information on risk management can be found in chapter 4 of the TIBER-EU framework.
Test Summary Report + 360 Feedback Report + Remediation Plan (8 weeks)
Draft the Test Summary Report (TSR) | CTL | Not started | • Final draft TSR | • The TSR should be delivered by the entity to the TM within eight weeks after the TM has sent the notification of completed RTTR and BTTR assessment • The findings and learnings of the replay exercise and the purple teaming exercise will feed directly into the final TSR • The TSR must comply to the available guidance: TIBER-EU Test Summary Report Guidance • The TSR must include at least: - the parties involved; - the project plan; - the validated scope, including the rationale behind the inclusion or exclusion of CIFs and identified ICT systems, processes and technologies supporting the CIFs covered by the test; - selected scenarios and any significant deviation from the TTIR; - executed attack paths, and used TTPs; - captured and non-captured flags; - deviations from the RTTP, if any; - BT detections, if any; - PT in testing phase, where conducted and the related conditions; - leg-ups used, if any; - risk management measures taken; - identified vulnerabilities and other findings, including their criticality; - root cause analysis of successful attacks; - high level plan for remediation, linking the vulnerabilities and other findings, their root causes and remediation priority; - lessons derived from feedback received.
Approval of the TSR | CTL | Not started | • Final TSR | • The TM shall approve the TSR. • Since the management body of the entity is accountable for this document, it is recommended to also get approval of the C-level representative in the CT. • If the TM does not act as a TIBER or TLPT authority, the TSR also needs to be sent to the respective competent authority.
Draft the Remediation plan (RP) | CTL | Not started | • Final draft RP | • The RP should be delivered by the entity to the TM within eight weeks after the TM has sent the notification of completed RTTR and BTTR assessment • The findings and learnings of the replay and PT exercises will feed directly into the Remediation Plan • The RP must comply to the available guidance: TIBER-EU Remediation Plan Guidance • The elements to be covered in the RP are: - a description of the identified shortcomings; - a description of the proposed remediation measures and of their prioritisation and expected completion, including where relevant measure to improve the identification, protection, detection and response capabilities; - a root cause analysis; - the entity’s staff or functions responsible for the implementation of the proposed remediation measures or improvements; - the risks associated to not implementing the described measures and, where relevant, risks associated to the implementation of such measures
Approval of the RP | CTL | Not started | • Final RP | • The TM shall approve the RP. • Since the management body of the entity is accountable for this document, it is recommended to also get approval of the C-level representative in the CT. • If the TM does not act as a TIBER or TLPT authority, the TSR also needs to be sent to the respective competent authority.
Plan and host the 360 feedback meeting | TM | Not started | • 360 feedback meeting | • The 360 feedback meeting takes place after completion of the replay and PT exercises • The TM participates in the 360 feedback process steps, but is not obliged to provide feedback. • This meeting is focussed on providing feedback to all the stakeholders involved in the testing process and to reflect upon and improve their approach for future tests. • The meeting also creates the possibility to provide feedback on the testing process as well as the TIBER-EU framework. • The key topics to be covered in the 360 feedback meeting are: - which activities/deliverables could have been improved; - which aspects of the TIBER process worked well; - which aspects of the TIBER process could be improved; - any other feedback
Total closure phase |  | Incomplete

## Attestation
Attestation and result dissemination
Actions and description | Responsible | Status | Deliverables | Guidance
Dissemination TSR, RP and attestation
Dissemination of the TSR and RP to the TIBER/TLPT authority | CT | Not started | • TSR and RP | • If the TM does not act as a TIBER or TLPT authority, the TSR and RP also need to be sent to the respective competent authority.
Dissemination of the TSR and RP to non-participating TIBER/TLPT authority | CT | Not started | • TSR, RP and attestation | • In cases where other TCTs did not participate in the test, but there was mutual agreement to share the test results, the entity should share the TSR, RP and the attestation.
Provide the attestation | TM | Not started | • Attestation | • Once the TM (or TLPT authority) has approved the TSR and the RP, the TIBER authority provides an attestation confirming that the test was conducted in accordance wiht the core requirements of the TIBER-EU framework. • The issuing of the attestation concludes the TIBER/TLPT test. • The attestation can serve as a means of qualifying the test for mutual recognition among other autorities.
Total attestation |  | Incomplete

## Version + Abbr.
Version 2.1 | July 2026
Abbreviations
BT | Blue Team
BTTR | Blue Team Test Report
CIF | Critical or Important Function
CSP | Critical Service Provider
CT | Control Team
CTL | Control Team Lead
CTI | Cyber Threat Intelligence
DORA | Digital Operational Resilience Act
ESCB | European System of Central Banks
GTL | Generic Threat Landscape
HUMINT | Human Intelligence
ICT | Information and Communication Technology
OSINT | Open-Source Intelligence
PT | Purple Teaming
RTT | Red Team Testers
RTTP | Red Team Test Plan
RTTR | Red Team Test Report
TCT | TIBER Cyber Team
TIBER | Threat Intelligence-Based Ethical Red Teaming
TIP | Threat Intelligence Provider
TKC | TIBER-EU Knowledge Centre
TLPT | Threat Led Penetration Testing
TSR | Test Summary Report
TI | Threat Intelligence
TTIR | Targeted Threat Intelligence Report
TM | Test Manager
TTP | Tactics, Techniques and Procedures

## Dropdown (hidden)
Status | Threat Intelligence | Red teaming | Purple teaming | Gold teaming
Not applicable | T1 - Internal TI team / GTL | R1 - One scenario, assumed compromise | P1 - PT fundamentals | G1 - Walkthrough
Not started | T2 - Internal TI team / GTL + old TI report | R2 - One scenario, in-through-out | P2 - PT full | G2 - Tabletop exercise
In progress | T3 - RTP provides limited TI report | R3 - Two scenarios, assumed compromise |  | G3 - Simulation without counterplay
Done | T4 - TIP provides full TI report | R4 - Two scenarios, one assumed compromise, one in-through-out |  | G4 - Simulation with counterplay
|  | R5 - Two scenarios, in-through-out |  | G0 - Not applicable
R6 - Three scenarios, including scenario X
R7 - Custom built